TEAM TUTORIAL

Task-Driven Development

with Claude Code

From spec to shipping — one phase at a time

Sample Project: URL Shortener API & Dashboard

Baresquare — LLM Upskilling sessions

March 2026

# 1. What This Tutorial Covers

This tutorial walks you through a structured approach to building software with Claude Code. You start by writing a Business Requirements Document (BRD), then let Claude Code generate a detailed spec and task list from it. Each group of tasks forms a phase, and each phase produces a testable prototype delivered as a GitHub Pull Request. The task list doubles as both an implementation plan and a plan review checkpoint.

## 1.1 The Workflow at a Glance

| Step | Who Does It | Output |
| --- | --- | --- |
| Write the BRD (& optional architecture doc) | You (human) | brd.md (and architecture.md) with business goals, requirements, constraints |
| Generate the spec | Claude Code (plan mode) | spec.md with phases, requirements per phase, and deliverables |
| Review & approve the spec | You (human) | Approved spec (edit if needed, then proceed) |
| Generate the task list | Claude Code (plan mode) | tasks.md with detailed tasks per phase |
| Review & refine tasks (plan review) | You (human) | Approved task list — your implementation plan |
| Execute a phase | Claude Code (edit mode) | Working code + tests |
| Create a PR | Claude Code | GitHub PR for the phase |
| Test the prototype | You (human) | Go / no-go for next phase |

## 1.2 Why Phases?

Splitting work into phases gives you checkpoint moments where you can test the prototype, catch misunderstandings early, and adjust direction before Claude Code invests effort in the wrong path. Each phase is self-contained: it has its own branch, its own PR, and produces something you can run and verify.

💡 Key Principle Claude Code’s native task system (TaskCreate, TaskUpdate, TaskList) persists tasks across sessions and supports dependencies. You don’t need external tools, Ralph Wiggum loops, or custom scripts. The built-in system handles everything.

# 2. Prerequisites

- Claude Code installed and authenticated (run Claude in your terminal)

- Git installed and configured with your GitHub account

- A GitHub repository created for the tutorial project

- Node.js 18+ (for our sample project)

## 2.1 Initial Setup

# Create a new repo and clone it git clone https://github.com/tzamtzis/claude-code-task-workflow-tutorial.git cd claude-code-task-workflow-tutorial # Initialize the project npm init -y # Start Claude Code claude

# 3. Step 1: Write the BRD, Generate the Spec

The workflow starts with you, the human, writing a Business Requirements Document (BRD). This is a plain-language description of what you want to build and why. You can optionally include an architecture document if you have strong opinions about the tech stack or system design. Claude Code then uses these documents to generate a structured spec with phases.

💡 Why separate the BRD from the spec? - The BRD captures the “what” and “why” (business goals, user needs, constraints). - The spec captures the “how” (phases, endpoints, data models, deliverables). - You own the BRD. Claude Code generates the spec from it. This means you can focus on requirements without worrying about implementation details, and Claude Code can propose a technical plan you can review and adjust.

## 3.1 Sample BRD: URL Shortener

Below is the BRD we’ll use for this tutorial. It is already available with the file name BRD.md under the folder “docs”. Notice it describes business goals and user stories, not implementation details.

# URL Shortener — Business Requirements Document ## Business Goal We need an internal URL shortener so the marketing team can create branded short links for campaigns and track how many people click them. ## User Stories - As a marketer, I want to paste a long URL and get a short one back - As a marketer, I want to see how many times each short link was clicked - As a marketer, I want to see when and where clicks come from - As a marketer, I want to optionally choose a custom short code ## Constraints - Must be self-hosted (no third-party SaaS dependency) - Must have a web dashboard (not just an API) - Must handle at least 100 requests/second - Budget: 1 developer-week ## Out of Scope (for now) - User authentication / multi-tenancy - QR code generation - Link expiration

## 3.2 Optional: Architecture Document

If you have preferences about the tech stack or system design, include an architecture.md file. This is optional — if you omit it, Claude Code will propose an architecture as part of the spec. The following content is already available under the “docs” folder with the name Architecture.md.

# URL Shortener — Architecture Notes ## Tech Stack - Backend: TypeScript + Express - Database: SQLite (simple, no external DB server needed) - Frontend: React with Vite - Testing: vitest + supertest ## Deployment - Single Node.js process serving both API and static frontend - SQLite file stored in ./data/ directory ## API Design - RESTful, JSON request/response - Short codes: 7-character alphanumeric (nanoid)

## 3.3 Generate the Spec with Claude Code

Now let Claude Code turn your BRD (and architecture doc) into a structured specification. Enter plan mode (Shift + Tab) so Claude reads the documents without modifying anything, then use this prompt:

Read @brd.md and @architecture.md (if it exists). Generate a spec.md file that includes: - A brief overview of the project - The tech stack (from architecture.md, or propose one if not provided) - The work split into 2-4 phases, where: - Each phase has a branch name (e.g., phase-1/core-api) - Each phase lists specific, concrete requirements - Each phase has a Deliverable section describing what I can test - Phases build on each other (Phase 2 depends on Phase 1, etc.) - The first phase should produce a minimal but functional prototype - The last phase should deliver the complete product Save the result as spec.md in the project root.

## 3.4 What Claude Code Produces

Claude Code will generate a spec.md that looks like this (based on our sample BRD):

# URL Shortener — Project Spec ## Overview A simple URL shortener with an API and a dashboard UI. Stack: TypeScript, Express, SQLite, React (Vite). ## Phase 1: Core API (branch: phase-1/core-api) Build the REST API that can shorten URLs and redirect. - POST /api/shorten — accepts { url } and returns { shortCode, shortUrl } - GET /:shortCode — redirects to the original URL (HTTP 302) - GET /api/stats/:shortCode — returns { url, shortCode, clicks, createdAt } - SQLite database with a "urls" table - Input validation (valid URL format, max length 2048 chars) - Unit tests for all endpoints using vitest + supertest Deliverable: A running API I can test with curl or Postman. ## Phase 2: Dashboard UI (branch: phase-2/dashboard-ui) Build a React frontend that talks to the Phase 1 API. - Form to submit a URL and display the shortened result - Table showing all shortened URLs with click counts - Copy-to-clipboard button for each short URL - Auto-refresh stats every 30 seconds - Responsive layout (mobile-friendly) Deliverable: A working dashboard where I can create and view short URLs. ## Phase 3: Analytics & Polish (branch: phase-3/analytics) Add click tracking details and improve UX. - Track referrer, user-agent, and timestamp per click - Dashboard: expandable row showing click history per URL - Dashboard: simple bar chart of clicks-per-day (last 7 days) - Rate limiting: max 10 shorten requests per minute per IP - Custom short codes: optional { customCode } param in POST /api/shorten Deliverable: Full app with analytics I can demo to stakeholders.

## 3.5 Review & Approve the Spec

This is your first review checkpoint. Read spec.md carefully and verify:

- Does each phase map to the user stories in your BRD?

- Is the phase ordering logical? (e.g., API before UI, core features before polish)

- Are the deliverables of each phase concrete enough for you to test?

- Is anything missing or out of scope that crept in?

Edit spec.md directly if anything needs adjusting. Once you’re happy with it, proceed to task generation.

⚠️ Notice the pattern in the spec - Each phase specifies: a branch name, clear requirements, and a deliverable. - The deliverable describes what you will test before giving the go-ahead for the next phase. This is your checkpoint.

# 4. Step 2: Generate the Task List (Plan Review)

With your approved spec in place, the next step is to ask Claude Code to break it down into a detailed task list. This task list serves a dual purpose: it is both the implementation plan for Claude Code and your plan review document. By reviewing it before execution begins, you confirm that the approach is correct and complete.

## 4.1 Enter Plan Mode & Prompt

Stay in plan mode (Shift + Tab) and use this prompt. Note that we reference both the BRD and the spec documents so Claude Code has full context:

Read @brd.md, @architecture.md (if present), and @spec.md. Create a detailed task list based on the spec. For EACH phase, generate tasks that include: - A clear, specific title - A description of what needs to be implemented - Acceptance criteria (how to verify the task is done) - Dependencies on other tasks (if any) Cross-reference the BRD to ensure no user stories are missed. Save the result as tasks.md in the project root. Use checkboxes (- [ ]) so we can track completion. Number tasks within each phase (e.g., P1-T1, P1-T2, P2-T1).

## 4.2 What Claude Code Produces

Claude Code will analyze the spec and produce a tasks.md file. Below is what you should expect for Phase 1 (abbreviated). The full file will contain all phases.

# Task List — URL Shortener ## Phase 1: Core API Branch: phase-1/core-api ¦ PR target: main - [ ] **P1-T1: Project scaffolding** Description: Initialize TypeScript + Express project with vitest. Install dependencies: express, better-sqlite3, nanoid, vitest, supertest. Create tsconfig.json, src/ folder structure, and dev/build scripts. Acceptance: npm run build compiles without errors, npm test runs (0 tests ok). Dependencies: none - [ ] **P1-T2: Database layer** Description: Create SQLite database module with a "urls" table schema. Columns: id (auto-increment), originalUrl (text), shortCode (text unique), clicks (integer default 0), createdAt (datetime default now). Export functions: createUrl(), getUrlByCode(), incrementClicks(), getAllUrls(). Acceptance: Unit tests pass for all four DB functions. Dependencies: P1-T1 - [ ] **P1-T3: POST /api/shorten endpoint** Description: Implement the shorten endpoint. Validate URL format and max length. Generate a 7-character short code using nanoid. Return { shortCode, shortUrl }. Acceptance: Tests verify successful shorten, invalid URL rejection, duplicate handling. Dependencies: P1-T2 - [ ] **P1-T4: GET /:shortCode redirect** Description: Look up the original URL by short code and redirect with HTTP 302. Increment the click counter. Return 404 for unknown codes. Acceptance: Test verifies redirect, click increment, and 404 for bad codes. Dependencies: P1-T2 - [ ] **P1-T5: GET /api/stats/:shortCode endpoint** Description: Return stats object { url, shortCode, clicks, createdAt }. Return 404 for unknown codes. Acceptance: Tests verify stats response and 404 handling. Dependencies: P1-T2 - [ ] **P1-T6: Integration tests & cleanup** Description: Add end-to-end tests that exercise the full flow: shorten → redirect → check stats. Ensure test DB is isolated (use in-memory SQLite). Acceptance: npm test passes with all unit + integration tests green. Dependencies: P1-T3, P1-T4, P1-T5

## 4.3 Review the Task List (Your Plan Review)

This is the most important checkpoint in the entire workflow. The task list is your implementation plan — reviewing it now is equivalent to a plan review meeting. No code gets written until you approve this list. Verify:

- Are the tasks granular enough? Each task should take Claude Code 2–5 minutes.

- Are dependencies correct? A task should only depend on tasks whose output it needs.

- Are acceptance criteria testable? “It works” is not good enough. Prefer “npm test passes”.

- Does each phase produce a testable deliverable?

- Do the tasks cover every user story from the BRD? Cross-reference to check.

💡 Tip: Edit the task list before executing You can (and should!) edit tasks.md directly. Add missing tasks, reword acceptance criteria, adjust dependencies. This is your blueprint — Claude Code will follow it precisely, so invest time here to save time later.

# 5. Step 3: Execute Phase by Phase

Now comes the execution. You’ll work through one phase at a time. For each phase, Claude Code creates a branch, executes every task, and produces a PR.

## 5.1 Start a Phase

Switch to edit mode (Shift + Tab until you see “Edit”) and use this prompt:

We are starting Phase 1 of the URL Shortener project. 1. Create and checkout a new branch: phase-1/core-api 2. Read @tasks.md and create native tasks (using TaskCreate) for all Phase 1 items. Set dependencies using addBlockedBy. 3. Work through each task in order: - Mark the task in_progress when you start - Implement the code - Run the acceptance criteria (e.g., run tests) - If tests pass, mark the task completed and update tasks.md (check off the box) - If tests fail, fix the issue before moving on - Commit after each completed task with message: "P1-Tx: <title>" 4. After all tasks are done, push the branch and stop.

## 5.2 What Happens During Execution

Claude Code will work through the tasks one by one. You’ll see the native task panel (Ctrl+T to toggle) updating in real time:

Tasks (Phase 1): [Ctrl+T to toggle] ✓ P1-T1: Project scaffolding completed ✓ P1-T2: Database layer completed ○ P1-T3: POST /api/shorten endpoint in_progress ● – P1-T4: GET /:shortCode redirect pending (blocked by P1-T2) – P1-T5: GET /api/stats/:shortCode pending (blocked by P1-T2) – P1-T6: Integration tests & cleanup pending (blocked by P1-T3,T4,T5)

⚠️ Let Claude Code finish the phase uninterrupted - Resist the urge to interrupt mid-phase unless something is clearly wrong. - The task system ensures Claude Code knows what’s done and what’s next. - If you must intervene, Claude Code will pick up from the last completed task.

## 5.3 Create the PR

Once all Phase 1 tasks are completed, ask Claude Code to create and review the PR:

All Phase 1 tasks are complete. Please: 1. Push the branch phase-1/core-api to origin 2. Create a GitHub PR targeting the “main” branch 3. Review the PR changes and suggest improvements/fixes

## 5.4 Test the Prototype

This is your human checkpoint. Pull the branch locally and verify the deliverable:

# Pull the PR branch and test it yourself git checkout phase-1/core-api npm install npm run build npm test # Manual smoke test npm run dev curl -X POST http://localhost:3000/api/shorten \ -H "Content-Type: application/json" \ -d '{"url": "https://baresquare.com"}' # Try the redirect curl -v http://localhost:3000/<shortCode>

If everything looks good: merge the PR to main and proceed to Phase 2. If something is off, leave PR comments and ask Claude Code to address them before merging.

# 6. Step 4: Repeat for Each Phase

After merging Phase 1, start a new Claude Code session (or /clear the current one) for a fresh context window, then repeat the same pattern:

# Start clean for Phase 2 git checkout main git pull claude # Then prompt: We are starting Phase 2 of the URL Shortener project. Read @brd.md, @spec.md, and @tasks.md for context. 1. Create and checkout branch: phase-2/dashboard-ui 2. Create native tasks for all Phase 2 items with dependencies 3. Work through each task in order (same rules as Phase 1) 4. Commit after each task, push when all done

## 6.1 The Full Phase Lifecycle

| Action | Who | Tool / Method |
| --- | --- | --- |
| Checkout main, pull latest | You | git checkout main && git pull |
| Start Claude Code fresh | You | claude (new session or /clear) |
| Prompt for the phase | You | Natural language prompt |
| Create branch | Claude Code | git checkout -b phase-x/... |
| Create tasks with deps | Claude Code | TaskCreate + addBlockedBy |
| Execute tasks one-by-one | Claude Code | Code, test, commit per task |
| Push branch | Claude Code | git push -u origin phase-x/... |
| Create PR | Claude Code | gh pr create |
| Test the prototype | You | Manual + automated testing |
| Merge PR | You | GitHub UI or gh pr merge |

# 7. Configuring CLAUDE.md for This Workflow

To make Claude Code follow this workflow automatically, add a CLAUDE.md file to your project root. This acts as persistent instructions that Claude Code reads at the start of every session. You can get a first version of this file using Claude’s /init command and then enrich with additional information depending on your preferences.

# CLAUDE.md This file provides guidance to Claude Code (claude.ai/code) when working with code in this repository. ## Project URL Shortener — TypeScript + Express + React (Vite) + SQLite ## Project Documents - brd.md — Business requirements (the why and what) - architecture.md — Tech stack and design decisions (optional) - spec.md — Generated from BRD; defines phases and deliverables - tasks.md — Generated from spec; detailed task list per phase ## Development Workflow - Always read brd.md, spec.md, and tasks.md before starting any work - Work in phases. Each phase = one branch = one PR targeting main - Use native tasks (TaskCreate) with dependencies for each phase - Mark tasks in_progress before starting, completed only after verification - Run tests (npm test) as part of every task’s acceptance criteria - Commit after each completed task: "Px-Tx: <title>" - Update tasks.md to check off completed items - Never skip ahead to the next phase without explicit approval ## Code Standards - TypeScript strict mode - All functions must have JSDoc comments - All endpoints must have corresponding test files - Use async/await, never raw callbacks - Import order: node built-ins, external deps, local modules

# 8. Tips & Best Practices

## 8.1 Writing Good Tasks

| Bad Task Examples | Good Task Examples |
| --- | --- |
| Set up the backend | P1-T1: Initialize TS + Express with vitest, create folder structure, verify build |
| Add database stuff | P1-T2: Create SQLite URLs table with schema, export CRUD functions, add unit tests |
| Make it work | P1-T6: Integration test: shorten → redirect → stats flow, verify click count increments |
| Fix bugs | P2-T5: Fix CORS error when dashboard calls API on different port, add test for preflight |

## 8.2 When Things Go Wrong

- Tests fail: Don’t panic. Claude Code will attempt to fix failures automatically before marking a task complete. If it’s stuck, give it a hint: “The test failure is because X, try Y.”

- Wrong direction: Stop the phase, leave a PR comment explaining the issue, and start fresh. The code is on a branch — main is safe.

- Context window fills up: Use /clear and start a new session. The tasks persist (native tasks at ~/.claude/tasks/ and your tasks.md in the repo), so Claude Code can resume from the last completed task.

- Phase scope creep: If you realize a phase needs more work, add tasks to tasks.md and re-prompt. Don’t try to cram extra work into the current prompt.

## 8.3 Useful Claude Code Commands

| Command | What It Does |
| --- | --- |
| Shift + Tab | Cycle between Plan / Edit modes |
| Ctrl + T | Toggle native task list visibility |
| /clear | Clear context for a fresh session |
| /compact | Summarize conversation to free context space |
| /plan | Enter plan mode (read-only exploration) |
| /init | Create/Update Claude.md file for the active folder with Claude code instructions |
| Escape | Cancel Claude Code’s current action |

# 9. Quick-Start Checklist

Use this checklist when applying this workflow to any new project:

- Create a GitHub repo and clone it locally

- Write brd.md with business goals, user stories, and constraints

- Optionally write architecture.md with tech stack and design preferences

- Add a CLAUDE.md with your workflow rules and code standards

- Start Claude Code in plan mode, prompt it to generate spec.md from the BRD

- Review spec.md: check phases, deliverables, and coverage of user stories

- Prompt Claude Code (still in plan mode) to generate tasks.md from the spec

- Review tasks.md as your plan review: verify granularity, deps, and acceptance criteria

- Switch to edit mode, prompt Claude Code to start Phase 1

- Watch the task panel (Ctrl + T), let Claude Code work through the tasks

- After phase completion: push branch, create PR

- Test the prototype yourself (the deliverable from the spec)

- Merge the PR if satisfied, or leave comments and iterate

- Start a fresh Claude Code session (/clear or new terminal)

- Repeat steps 9–14 for each subsequent phase

# 10. What Your Git History Looks Like

After completing all three phases, your Git history will have a clean, reviewable structure:

main │ ├── Merge PR #1: Phase 1 - Core API │ ├── P1-T1: Project scaffolding │ ├── P1-T2: Database layer │ ├── P1-T3: POST /api/shorten endpoint │ ├── P1-T4: GET /:shortCode redirect │ ├── P1-T5: GET /api/stats/:shortCode endpoint │ └── P1-T6: Integration tests & cleanup │ ├── Merge PR #2: Phase 2 - Dashboard UI │ ├── P2-T1: Vite + React setup with proxy to API │ ├── P2-T2: URL submission form component │ ├── P2-T3: URL list table with click counts │ ├── P2-T4: Copy-to-clipboard functionality │ └── P2-T5: Auto-refresh + responsive layout │ └── Merge PR #3: Phase 3 - Analytics & Polish ├── P3-T1: Click tracking schema + migration ├── P3-T2: Click events API endpoint ├── P3-T3: Expandable click history rows ├── P3-T4: Clicks-per-day bar chart ├── P3-T5: Rate limiting middleware └── P3-T6: Custom short codes support

Each PR is a reviewable, testable increment. Each commit maps to exactly one task. This makes it easy to bisect issues, review changes, and understand what was built and when.

# 11. Further Reading & Advanced Topics

Once you feek comfortable with the phase-based workflow above, the resources below go deeper into task orchestration, autonomous loops, and multi-agent patterns.

## 11.1 Official Anthropic Resources

| Resource | Format | What You’ll Learn |
| --- | --- | --- |
| Claude Code in Action (Coursera) https://www.coursera.org/learn/claude-code-in-action | Free course (video + labs) | End-to-end Claude Code fundamentals: setup, plan mode, hooks, subagents, and custom commands. Good baseline for the whole team. |
| Common Workflows — Official Docs https://code.claude.com/docs/en/common-workflows | Documentation | Practical workflow recipes for debugging, refactoring, testing, PR creation, worktrees, and session management. |
| Best Practices — Official Docs https://code.claude.com/docs/en/best-practices | Documentation | Higher-level patterns: prompt structure, CLAUDE.md design, context management, and when to use plan vs edit mode. |

## 11.2 Task Management Deep Dives

| Resource | Format | What You’ll Learn |
| --- | --- | --- |
| Native Task Management Guide https://claudefa.st/blog/guide/development/task-management | Blog post | Comprehensive reference for TaskCreate, TaskUpdate, dependencies, blockers, multi-session sync via CLAUDE_CODE_TASK_LIST_ID, and migration from the older TodoWrite system. |
| Todo Workflow Fundamentals https://claudefa.st/blog/guide/development/todo-workflows | Blog post | How to structure task descriptions so Claude Code follows them precisely. Covers common pitfalls: tasks too generic, wrong order, missing steps. |
| DeepWiki: Task Management Reference https://deepwiki.com/FlorianBruniaux/claude-code-ultimate-guide/8-task-management | Wiki | Technical deep dive into the Tasks API internals: storage architecture (~/.claude/tasks/), JSON schema, field visibility limitations, and DAG execution. |

## 11.3 Autonomous & Overnight Workflows

| Resource | Format | What You’ll Learn |
| --- | --- | --- |
| Ralph Wiggum Technique https://claudefa.st/blog/guide/mechanics/ralph-wiggum-technique | Blog post | The original autonomous loop pattern: stop hooks, completion promises, and verification-first workflows. Useful when you want Claude Code to work AFK for hours. |
| 11 Tips for AI Coding with Ralph Wiggum https://www.aihero.dev/tips-for-ai-coding-with-ralph-wiggum | Blog post | Practical tips for writing prompts that converge. Covers the progression from interactive → planning → multi-phase → autonomous loops. |
| Ralph Loop QuickStart (Cole Medin) https://github.com/coleam00/ralph-loop-quickstart | GitHub repo | Hands-on starter kit using the bash-loop method (fresh context per iteration). Includes PRD generation, sandboxed execution, and cost control. |

## 11.4 Spec-Driven & Plan-Driven Patterns

| Resource | Format | What You’ll Learn |
| --- | --- | --- |
| Spec-Driven Development with Claude Code https://alexop.dev/posts/spec-driven-development-claude-code-in-action/ | Blog post | Real-world walkthrough of a large refactor: parallel research subagents, written specs, orchestrator + checker sessions, and the task system for context-efficient implementation. |
| Plan-Driven Development — DeepWiki https://deepwiki.com/FlorianBruniaux/claude-code-ultimate-guide/9.1-plan-driven-development | Wiki | The /plan workflow in depth: plan file structure, approval gates, the Explore → Plan → Implement → Commit cycle, and dual-instance planning patterns. |
| Spec Workflow Plugin (Pimzino) https://github.com/Pimzino/claude-code-spec-workflow | GitHub repo | npm-installable workflow plugin: Requirements → Design → Tasks → Implementation. Includes steering docs, validation agents, and 60-80% token reduction via context sharing. |

## 11.5 Video Tutorials & Walkthroughs

| Resource | Duration | What You’ll Learn |
| --- | --- | --- |
| 20 Tips to Master Claude Code (Peter Yang) https://creatoreconomy.so/p/20-tips-to-master-claude-code-in-35-min-build-an-app | 35 min | Builds a complete app on camera using the spec → todo → code cycle. Covers plan mode, output styles, milestone-based todo lists, and debugging. |
| Automate Your Life with Claude Code (Teresa Torres) https://creatoreconomy.so/p/automate-your-life-with-claude-code-teresa-torres | 50 min | Live demo of a markdown-based task management system with custom /today commands, automated research digests, and a 3-layer context architecture. |
| My Claude Code Workflow (Zhu Liang) https://thegroundtruth.media/p/my-claude-code-workflow-and-personal-tips | Written guide | Practitioner’s guide to ROADMAP.md + task files: one task per session, plan review before execution, and practical tips for context management. |

## 11.6 Community Collections

| Resource | What It Is |
| --- | --- |
| Awesome Claude Code https://github.com/hesreallyhim/awesome-claude-code | Curated list of skills, hooks, slash commands, agent orchestrators, and plugins. Good for discovering workflows your team can adopt. |
| Claude Code — Everything You Need to Know https://github.com/wesammustafa/Claude-Code-Everything-You-Need-to-Know | Comprehensive reference covering setup, prompt engineering, hooks, MCP servers, the BMAD method, and hands-on demos. Updated for Feb 2026. |
| AI Coding Daily (Povilas Korop) https://aicodingdaily.com | Weekly newsletters with Claude Code tutorials, workflow experiments, prompt recipes, and real-world project walkthroughs. |